## 📌 Today
5 CIRCLES HQ
OVERDUE TASKS | DUE TODAY | STUCK
LEADS TO CALL | CONTENT LATE | CLOSED YDAY
⚠️ FIX FIRST — overdue & stuck
TASK | WHO | DUE | STATUS
🔵 DUE TODAY
TASK | WHO | DUE | GIVEN BY
📞 CALL TODAY — follow-ups waiting
NAME | PHONE | PROGRAM | STATUS
🎬 CONTENT RUNNING LATE
TOPIC | ACCOUNT | PLANNED | STAGE
Add work in ✅ Tasks · log every lead in 📞 Leads · file 🌙 Day Close before you leave. This page fills itself — don't type here.

## ✅ Tasks
Task | Who | Due | Status | Given by | Given on | Done on | Notes
Edit & schedule Thursday's theta reel | Rahul Sarawagi | 2026-08-25 | Doing | Rahul Sarawagi | 2026-08-24 |  | (sample rows — replace with real work)
WhatsApp today's new ad leads before 1 pm | Rahul Sarawagi | 2026-08-26 | To do | Rahul Sarawagi | 2026-08-26
Fix classroom mic echo before Saturday session | Rahul Sarawagi | 2026-08-24 | Stuck | Rahul Sarawagi | 2026-08-22 |  | Vendor not answering — need a decision
Post Monday's market-myth carousel | Rahul Sarawagi | 2026-08-23 | Done | Rahul Sarawagi | 2026-08-21 | 2026-08-23

## 🎬 Content
Post date | Account | Format | Topic / hook | Stage | Owner | Link | Notes
2026-08-27 | 5 Circles | Reel | Theta: the rent you pay to hold hope | Edit | Rahul Sarawagi |  | (sample rows — replace with your calendar)
2026-08-25 | Traders Club | Post | Saturday session recap + photos | Shoot | Rahul Sarawagi
2026-08-29 | Rahul | Carousel | What my first loss taught me about sizing | Idea | Rahul Sarawagi

## 📞 Leads
Added on | Name | Phone | Source | Program | Status | Next follow-up | Notes
2026-08-25 | Aman Verma | 98765 43210 | Ad | Options Lab | New | 2026-08-26 | (sample rows — replace with real leads)
2026-08-23 | Priya S. | 91234 56780 | Webinar | Traders Club | Interested | 2026-08-28 | Wants Saturday batch details

## 🌙 Day Close
Date | Name | What I finished today | Stuck on (blank if nothing) | Tomorrow's #1 thing
2026-08-25 | Rahul Sarawagi | Recorded 2 reels, replied to 14 DMs, closed 1 admission |  | Call Aman about Options Lab

## 👥 Team
Name | Role | Phone | Filed day close yesterday?
Rahul Sarawagi | Founder
Formulas:
Filed day close yesterday? = IF([Name]="","",IF(COUNTIFS('🌙 Day Close'!$A:$A,TODAY()-1,'🌙 Day Close'!$B:$B,[Name])>0,"✔ yes","— no"))

## 📖 Read me
5 CIRCLES HQ — how this works
One sheet. No app, no login, no server, nothing to install. It lives in your Google Drive, opens in the Sheets app on every phone, and never expires.
THE DAILY LOOP
Morning — open 📌 Today. It shows what's overdue, what's due, which leads to call, and what content is late. Fix that list first.
During the day — when work moves, tap its Status dropdown: To do → Doing → Done. Truly blocked? Set it to Stuck — that's not failure, that's a flare. Stuck rows jump to the top of Today so someone helps you fast.
Evening — before you leave, add one row in 🌙 Day Close: what you finished, what you're stuck on, tomorrow's #1. Under a minute. Then send a ✅ in the WhatsApp group so everyone knows you closed.
THE TABS
📌 Today — fills itself, and it's locked so nobody breaks it. Don't type here.
✅ Tasks — one row per job. A task without a Due date and a Who is just a wish.
🎬 Content — every post across 5 Circles, Rahul, and Traders Club. Move the Stage as it progresses: Idea → Script → Shoot → Edit → Ready → Posted.
📞 Leads — every enquiry, same day it arrives. Set 'Next follow-up' and it will appear on Today when the day comes. A lead never chased is money burned on ads.
🌙 Day Close — one row per person per day. The founder reads this tab first.
👥 Team — add your people here FIRST (name, role, phone). Every 'Who' dropdown in the sheet reads from this list.
RULES THAT KEEP IT ALIVE
1. If it's not in the sheet, it doesn't exist. WhatsApp is for talking; this is for remembering.
2. Never delete rows — mark tasks Done, leads Not now. History is an asset.
3. Colours mean things: red tint = late, blue tint = today, green tint = done.
4. The sample rows (marked in Notes) are safe to replace with real work.
5. Anyone can see everything. That's the point — problems can't hide.
SETUP — 2 MINUTES, ONCE
1. 👥 Team → add everyone's name, role, phone.
2. Share (top-right) → add each person's Google email as Editor.
3. Everyone installs the Google Sheets app and stars ⭐ this file.
That's the whole deployment.